## Work plan
| Date added | Start date | End date | Work description | Work results | Next steps | Notes, struggles
| 20/01/2020 | 20/01/2020 | 20/01/2020 | LECTURE: module intro |  | Reread it at home and make some notes | Many unknown terms
| 20/01/2020 | 20/01/2020 | 24/01/2020 | Setup Matlab environment | Matlab tools installed | Learn matlab basics/fundamentals | Matlab installation is a long process
| 20/01/2020 | 20/01/2020 | 24/01/2020 | Download data and create project folder | Downloaded all data, extracted to ./data | Try to read and understand the data | Files at this moment doesn’t look meaningful
| 27/01/2020 | 28/01/2020 | 29/01/2020 | Play with data files using ncread | Can read/open and save data to variable
| 27/01/2020 | 28/01/2020 |  | Outline the project plan
| 27/01/2020 | 27/01/2020 | 27/01/2020 | LECTURE: specifications |  | Develop project plan, start working on specification | Never done specification before, it's new
| 29/01/2020 | 30/01/2020 |  | Turn project outline into SMART list
| 29/01/2020 | 30/01/2020 |  | Download and fill specifiations document
| 29/01/2020 | 29/01/2020 |  | Read articles about big data techniques and try to write some code
| 29/01/2020 | 29/01/2020 | 29/01/2020 | Learn Matlab basics, matrixes | Can create/read/update 3 dimentional matrix as well as create functions | Use this knowledge to build algorithms
| 31/01/2020 | 2020-02-02 | 2020-02-02 | Create separate functions to show nc file specs | Functions are defined in separate files | Explore nc files contents | Needed to read docs about matlab functions
| 31/01/2020 | 2020-02-02 | 2020-02-02 | Create separate functions to read nc models by name or by id 1-7 or all models at once | Functions are defined in separate files | Use functions models where needed | Needed to read docs for splitting functions in files
| 2020-02-02 | 2020-02-02 | 2020-02-02 | Analyze lecturer's mail related to sub-project 3. Compare the traditional ensemble with CBE
| 2020-03-02 | 2020-03-02 | 2020-03-02 | LECTURE:
week4 | 2020-10-02 | 2020-10-02 | 2020-10-02
week5 | 17/02/2020 | 17/02/2020 | 17/02/2020
week6 | 24/02/2020 | 24/02/2020 | 24/02/2020
week7 | 2020-02-03 | 2020-02-03 | 2020-02-03
week8 | 2020-09-03 | 2020-09-03 | 2020-09-03
week9 | 16/03/2020 | 16/03/2020 | 16/03/2020

## Facts
Project requires analysis and displays of the results
Data has 14 data models but we will use only 7 of them
The data corver chemistry species: CO2, H2O, O3, PM2.5,PM10
This project uses O3 only
Grid is spaced at 0.1* lon and lat. This results 700x400 cover in Europe
Data format: NetCDF (standard in climate science)
By using DDC clustering algorithm the accuracy of climate model ensembles can be improved up to 18 % (Hyde and Angelov 2014)
Requirements: use big data techniques to reduce processing time to <2hours
Big data techniques: sub-spacing, parallel processing, display of big data
Definition | Ensemble medeling is the process of running 2 or more related but different analytical models and then synthesizing the results into a single score in order to improve the accuracy of predictive analytics | https://searchbusinessanalytics.techtarget.com/definition/Ensemble-modeling | .
Definition | CBE is a Cluster Based Ensemble
Definition | DDC is a Data Density-based Clustering | https://cumoodle.coventry.ac.uk/course/view.php?id=70387&sectionid=1011258 | .

## Projects
Suggested Sub-Projects | Description | Difficulty
Cluster Based Ensembe | Focus on parallel processing the CBE calculations; DDC clustering algorithm is available in Matlab only | 10 out of 10
Ensemble Comparisons | Focus on comparisons between the CBE and simple ensembles | 8 out of 10
Visualization | Focus on visualizing the results in an east to interpret format | 4 out of 10
Speed comparison | Involves re-writing DDC clustering algorithm in different languages and running tests to compare the execution time | x out of 10