## Work plan
Date added | Start date | End date | Work description | Work results | Next steps | Notes, struggles
20/01/2020 | 20/01/2020 | 20/01/2020 | LECTURE: module intro |  | Reread it at home and make some notes | Many unknown terms
20/01/2020 | 20/01/2020 | 24/01/2020 | Setup Matlab environment | Matlab tools installed | Learn matlab basics/fundamentals | Matlab installation is a long process
20/01/2020 | 20/01/2020 | 24/01/2020 | Download data and create project folder | Downloaded all data, extracted to ./data | Try to read and understand the data | Files at this moment doesn’t look meaningful
27/01/2020 | 28/01/2020 | 29/01/2020 | Play with data files using ncread | Can read/open and save data to variable
27/01/2020 | 28/01/2020 | 28/01/2020 | Outline the project plan | Wrote down on paper what major steps will be made | Format those steps into tasks and supplement this doc with tasks | Took me a long time. I am a bit behind with this task
27/01/2020 | 27/01/2020 | 27/01/2020 | LECTURE: specifications |  | Develop project plan, start working on specification | Never done specification before, it's new
29/01/2020 | 30/01/2020 |  | Turn project outline into SMART list |  |  | Some unexpeted delays due to the lack of fundamental matlab knowledge
29/01/2020 | 30/01/2020 | 19/01/2020 | Download and fill specifiations document | Specifications document is created | Ask for feedback from the turor | This task required the most time to complete
29/01/2020 | 29/01/2020 |  | Read articles about big data techniques and try to write some code
29/01/2020 | 29/01/2020 | 29/01/2020 | Learn Matlab basics, matrixes | Can create/read/update 3 dimentional matrix as well as create functions | Use this knowledge to build algorithms
31/01/2020 | 05/02/2020 | 05/02/2020 | Create separate functions to show nc file specs | Functions are defined in separate files | Explore nc files contents | Needed to read docs about matlab functions
31/01/2020 | 05/02/2020 | 05/02/2020 | Create separate functions to read nc models by name or by id 1-7 or all models at once | Functions are defined in separate files | Use functions models where needed | Needed to read docs for splitting functions in files
04/02/2020 | 05/02/2020 | 06/02/2020 | Analyze lecturer's mail related to sub-project 3. Compare the traditional ensemble with CBE
02/02/2020 | 02/02/2020 | 02/02/2020 | LECTURE: code planning | I stayed till the end without break. Find out that I can use clutering to define which model is closiest to average(mean)
07/02/2020 | 07/02/2020 | 07/02/2020 | LECTURE: code planning (other group) | Had a great talk with a lecturer. Visualized my idea, found out the difference between CBE and DDC relations. Realised that given CBE data is normalized (x10^-8 is taken out from org data) | Transform my sequential simple mean ensemble function to parallel processed. Includes data deviding into subsets. Create flowchart, PSEUDOCODE | I have a good idea about the project, but many tasks are waiting to be done
04/02/2020 | 04/02/2020 | 11/02/2020 | Learn to measure execution time in matlab | Its just 2 commands needed: tic and toc | implement some sequential and parallel processign and compare results
04/02/2020 | 04/02/2020 | 04/02/2020 | Map the matrix indexes to coordinates when drawing the plot | Now heat map plots LON LAT values, instead of 1-400x1-700 |  | I had to read coordinates from the data file and pass it to a plot function
10/02/2020 | 10/02/2020 | 10/02/2020 | Create a flowchart | Flowchart made in .project and .jpg formats | You this chart to create the code. Once code is created, write pseudocode | Hard to find good software to draw (time-consuming)
10/02/2020 |  |  | Create Pseudocode examples
11/02/2020 | 16/02/2020 | 17/02/2020 | Use flowchart to create tasks in logbook | Tasks were added down below | Finish the tasks before the separator line and then continue
11/02/2020 | 17/02/2020 | 17/02/2020 | Analyze moodle code for parallel processing, make notes | Now I understand how I can create parallel processing. PAR is faster |  | There is advanced Parallel processing which can win so extra time compared to regular parallel processing
11/02/2020 |  |  | Analyze moodle code for figure drawing and make some notes
20/02/2020 | 20/02/2020 | 21/02/2020 | Sectionize the index file by %% comments using flowchat to facilitate code readibility | Comments added to make code sections which helps to indentify which flowchart part it belongs to | Start implementing the code - flowchart | No difficulties
11/02/2020 | 11/02/2020 | 2020-11-02 | Generate README page including: installation guide, folder/file description, idea explanation, output examples | This simple README guide lets quickly descripbe this project for people involved in it | After some time, don’t forget to improve it as things change quite often | Matlab doesn’t support MD files
11/02/2020 | 22/02/2020 | Closed | Transform CBE from .csv files to .mat | DFD changed
22/02/2020 | 22/02/2020 | 22/02/2020 | Load 7 models and calc SME (mean) | Data loaded into var SME | use to calculate bias with ORG | Parallel processing takes more time than sequential, possibly due to small data set
22/02/2020 | 22/02/2020 | 22/02/2020 | Load Observation values from /data/org | Data loaded into var ORG
22/02/2020 | 22/02/2020 | 22/02/2020 | Load CBE values from /data/cbe | Data loaded into var CBE | use to calculate bias with ORG
11/02/2020 | 22/02/2020 | Closed | Write a function to load ensembles: CBE or SME (add parameter to determine which one) where data is saved in "/data/x.mat" file | DFD changed
11/02/2020 | 22/02/2020 | Closed | Implement parallel processed simple mean ensemble algorithm (add func param: saveToFile: bool) | Parallel processing is inefficient to use with small data set | Time measuarments (tic,toc) shows that sequential code is faster
11/02/2020 | 2020-12-02 | 21/02/2020 | Ask teacher what he means by: "compare CBE/SME (bias) with the observations" | Answered the question on 21/02/2020. Observation is the real measurments that were used to prove that data clustering is more accurate than mean model |  | Lack of definions in module introduction dragged my progress a bit down as I was unable to develop
11/02/2020 |  |  | Write an algorithm to calculate difference (bias) between ORG and SME (in parallel)
11/02/2020 |  |  | Write an algorithm to calculate difference (bias) between ORG and CBE (in parallel)
11/02/2020 |  |  | Write a function to draw a Ozone map in Europe region where args are: matrix/model 698x398
22/02/2020 |  |  | Improve map plot by adding coordinate Axis values, and title
11/02/2020 |  |  | Save observation figures to file (expected 5)
11/02/2020 | 14/02/2020 | 21/02/2020 | Reflect my project specification with a friend and lecturer | Lecturer took a look, positive review | Develop the code
11/02/2020 | 22/02/2020 | Closed | Analyze DDC algorithm, understand its inputs and outpus and play with it | My project doesn't involve using DDC algorithm. I get CBE model by itself | DDC return value (points assigned to clusters) is beeing used to calculate a CBE
20/02/2020 | 21/02/2020 | 21/02/2020 | LECTURE: project development | Lecturer explained how Data Density algorithm works and how to use the results to generate CBE. Loaded 3 different models into matlab: CBE (scaling was used), SME and Observatiosns. Found out that Orig files given by teacher are different from my generated SME and this is potentially an Observations data which I am going to use as well to show that CBE is more accurate compared to SME | Use SME, CBE and Observations to calculate biases. Also, generate new flowchart due to fact updates (Orig is possibly an Observations data) | Orig data files are quite different compared to the generated mean ensemble by myself. This bring a little comfusion. I am going to assume that Orig data is Observations and use it in my project, which makes the project more difficult as I have to handle more data
21/02/2020 | 21/02/2020 | 22/02/2020 | Refactor Data Flow Diagram | DFD can be found in images directory named flowchart2.png | Use updated DFD to create code, refactor tasks | No difficulties
22/02/2020 |  |  | Clean up the data files (remove unused), clean up the code
22/02/2020 |  |  | Update readme guide to run the project

## Facts
Project requires analysis and displays of the results
Data has 14 data models but we will use only 7 of them
The data corver chemistry species: CO2, H2O, O3, PM2.5,PM10
This project uses O3 only
Grid is spaced at 0.1* lon and lat. This results 700x400 cover in Europe
Data format: NetCDF (standard in climate science)
By using DDC clustering algorithm the accuracy of climate model ensembles can be improved up to 18 % (Hyde and Angelov 2014)
Requirements: use big data techniques to reduce processing time to <2hours
Big data techniques: sub-spacing, parallel processing, display of big data
Definition | Ensemble medeling is the process of running 2 or more related but different analytical models and then synthesizing the results into a single score in order to improve the accuracy of predictive analytics | https://searchbusinessanalytics.techtarget.com/definition/Ensemble-modeling | .
Definition | CBE is a Cluster Based Ensemble
Definition | DDC is a Data Density-based Clustering | https://cumoodle.coventry.ac.uk/course/view.php?id=70387&sectionid=1011258 | .

## Projects
Suggested Sub-Projects | Description | Difficulty
Cluster Based Ensembe | Focus on parallel processing the CBE calculations; DDC clustering algorithm is available in Matlab only | 10 out of 10
Ensemble Comparisons | Focus on comparisons between the CBE and simple ensembles | 8 out of 10
Visualization | Focus on visualizing the results in an east to interpret format | 4 out of 10
Speed comparison | Involves re-writing DDC clustering algorithm in different languages and running tests to compare the execution time | x out of 10